## Agile Documentation
ExamGuard - Agile Documentation
Project: ExamGuard ¦ Agile work items, sprint tracking and completion status
S.No | Sprint | Module / Feature | User Story / Task | Priority | Status | Acceptance Criteria / Expected Outcome | Remarks
1 | Sprint 1 | Project Setup | Set up Flask application structure and virtual environment | High | Completed | Application structure is created and dependencies can be installed. | Foundation completed
2 | Sprint 1 | Authentication | Implement student and administrator authentication | High | Completed | Valid users can access the appropriate application functionality. | Role separation implemented
3 | Sprint 1 | Database | Integrate SQLAlchemy and application data models | High | Completed | Required user, examination and monitoring data can be stored. | Database layer integrated
4 | Sprint 2 | Online Examination | Implement examination interface and question handling | High | Completed | Students can access questions and provide answers. | Core examination workflow
5 | Sprint 2 | Submission | Implement examination answer submission | High | Completed | Students can submit completed examinations. | Submission workflow integrated
6 | Sprint 3 | Face Monitoring | Integrate OpenCV-based face monitoring | High | Completed | Camera frames can be processed for face-related monitoring. | Computer vision module
7 | Sprint 3 | Face Absence | Detect and record face-absence events | High | Completed | Configured face-absence events are recorded. | Threshold: 60 seconds
8 | Sprint 3 | Multiple Face | Detect multiple faces during an examination | High | Completed | Multiple-face events are detected and recorded. | Violation weight: 15
9 | Sprint 4 | Browser Monitoring | Detect examination tab switching | High | Completed | Tab-switch events are recorded for integrity analysis. | Violation weight: 8
10 | Sprint 4 | Focus Monitoring | Detect browser focus loss | High | Completed | Focus-loss events are recorded. | Violation weight: 5
11 | Sprint 4 | Audio Monitoring | Implement configured audio-spike monitoring | Medium | Completed | Configured audio events are recorded. | Violation weight: 6
12 | Sprint 5 | Violation Analysis | Apply configured weights to monitoring events | High | Completed | Monitoring events contribute to the violation analysis. | Weighted scoring implemented
13 | Sprint 5 | Integrity Analytics | Calculate examination integrity information | High | Completed | Integrity information is available for administrator review. | Threshold-based analysis
14 | Sprint 5 | Admin Dashboard | Provide administrator access to examination and monitoring information | High | Completed | Administrators can review relevant examination information. | Admin functionality integrated
15 | Sprint 6 | Report Generation | Generate structured examination integrity reports | Medium | Completed | Collected examination information can be converted into a narrative report. | LangChain component
16 | Sprint 6 | Testing | Test examination, monitoring and administrative workflows | High | Completed | Major workflows operate without blocking errors. | Functional testing completed
17 | Sprint 6 | Documentation | Prepare project, installation and user documentation | High | Completed | Repository contains required project documentation. | GitHub submission preparation
18 | Future | Anti-Spoofing | Improve face verification and anti-spoofing capabilities | Medium | Planned | Enhanced mechanisms reduce false or unauthorized face events. | Future enhancement
19 | Future | Scalability | Improve support for larger numbers of simultaneous examinations | Medium | Planned | Application can support increased examination load. | Future enhancement